## Build Days
YBM.
Build Days Calculator
What your contract actually promised, and where you are against it.
Fill the four blue cells. Everything else calculates itself.
YOUR CONTRACT
Construction start date | 2026-04-20 | The date the contract says construction starts.
Contract build days | 240 | As written in the contract. Check whether it says calendar or working days.
Extension of time days approved | 0 | Only days the builder has given you in writing.
Days lost to weather or trade delay | 0 | Your own record, for comparison.
WHERE YOU STAND
Original contract finish date | 2026-12-16 | What you were promised when you signed.
Revised finish date with EOTs | 2026-12-16 | What the builder is now contractually working to.
Days since construction started | 182
Days remaining on contract | 58 | A negative number means the build is past its contract date.
Percentage of contract time used | 75.83%
Status | Within contract | If this says past contract date, check your liquidated damages clause.
If the build is past its contract date and no extension has been approved in writing, liquidated damages may be payable to you. Check the clause, then put the request in writing.